## Sheet1
task_id | Forecast | STATUS_CODE | Baseline date | TASK_CODE | TASK_NAME | August
1 | 09-08-2020 | Completed | 2020-06-09 | CS010420 | Stage Gate P7
2 | 09-03-2019 | Completed | 2019-06-07 | CQPM10009390 | (15) OTD Milestones - System Commissioning Complete (Stage 2)
4 | 07-04-2019 | Completed | 2019-06-07 | CQPM10009380 | (14) OTD Milestones - Subsystem Pre-Commissioning Complete
5 | 05-05-2019 | Completed | 2019-06-05 | CQPM10001200 | (13) OTD Milestones - Installation Completed
6 | 31/02/2018 | Completed | 2018-01-31 | CQPM10009370 | (09) OTD Milestones - Detailed Engineering Complete
7 | 27-01-2014 | Completed | 2014-09-26 | CQPM10001150 | (10) OTD Milestones - Manufacture Of All Long Lead Items Complete
8 | 28-11-2013 | Completed | 2013-10-28 | CQPM10001130 | (07) OTD Milestones - Civil Design Issued To Customer
9 | 18-05-2012 | Completed | 2012-05-18 | CQPM10001190 | (12) OTD Milestones - Building Ready For Equipment Installation
10 | 05-04-2012 | Completed | 2012-04-05 | CQPM10009360 | (11) OTD Milestones - FAT of Critical Long Lead Items Complete
11 | 23-12-2011 | Completed | 2011-12-23 | CQPM10009350 | (06) OTD Milestones - Protection & Control System Base Design Complete
12 | 10-01-2011 | Completed | 2011-01-10 | CQPM10001140 | (08) OTD Milestones - Civil Contractor Mobilised On Site
13 | 10-01-2011 | Completed | 2011-01-10 | CQPM70210 | Summary Milestone - Start on site (Stage Gate)
14 | 15-12-2010 | Completed | 2010-12-13 | CQPM10001120 | (04) OTD Milestones - Overall Base Design Completed
15 | 04-09-2010 | Completed | 2010-09-24 | CQPM10001110 | (05) OTD Milestones - P.O for Long Lead-Critical Items Issued
16 | 10-09-2010 | Completed | 2010-09-20 | CQPM10009340 | (03) OTD Milestones - Project Execution Plan (PEP) In Place
17 | 20-06-2010 | Completed | 2010-09-20 | CQPM10009330 | (02) OTD Milestones - Project Management Team Mobilised
18 | 20-05-2010 | Completed | 2010-09-20 | CQPM10001100 | (01) OTD Milestones - Contract Effective Date
task_id | Forecast | STATUS_CODE | Baseline date | TASK_CODE | TASK_NAME | September
1 | 09-08-2020 | Completed | 2020-06-09 | CS010420 | Stage Gate P7
2 | 09-03-2019 | Completed | 2019-06-07 | CQPM10009390 | (15) OTD Milestones - System Commissioning Complete (Stage 2)
4 | 07-04-2019 | Completed | 2019-06-07 | CQPM10009380 | (14) OTD Milestones - Subsystem Pre-Commissioning Complete
5 | 05-05-2019 | Completed | 2019-06-05 | CQPM10001200 | (13) OTD Milestones - Installation Completed
6 | 31/02/2018 | Completed | 2018-01-31 | CQPM10009370 | (09) OTD Milestones - Detailed Engineering Complete
7 | 27-01-2014 | Completed | 2014-09-26 | CQPM10001150 | (10) OTD Milestones - Manufacture Of All Long Lead Items Complete
8 | 28-11-2013 | Completed | 2013-10-28 | CQPM10001130 | (07) OTD Milestones - Civil Design Issued To Customer
9 | 18-05-2012 | Completed | 2012-05-18 | CQPM10001190 | (12) OTD Milestones - Building Ready For Equipment Installation
10 | 05-04-2012 | Completed | 2012-04-05 | CQPM10009360 | (11) OTD Milestones - FAT of Critical Long Lead Items Complete
11 | 23-12-2011 | Completed | 2011-12-23 | CQPM10009350 | (06) OTD Milestones - Protection & Control System Base Design Complete
12 | 10-01-2011 | Completed | 2011-01-10 | CQPM10001140 | (08) OTD Milestones - Civil Contractor Mobilised On Site
13 | 10-01-2011 | Completed | 2011-01-10 | CQPM70210 | Summary Milestone - Start on site (Stage Gate)
14 | 13-12-2010 | Completed | 2010-12-13 | CQPM10001120 | (04) OTD Milestones - Overall Base Design Completed
15 | 24-09-2010 | Completed | 2010-09-24 | CQPM10001110 | (05) OTD Milestones - P.O for Long Lead-Critical Items Issued
16 | 20-09-2010 | Completed | 2010-09-20 | CQPM10009340 | (03) OTD Milestones - Project Execution Plan (PEP) In Place
17 | 20-09-2010 | Completed | 2010-09-20 | CQPM10009330 | (02) OTD Milestones - Project Management Team Mobilised
18 | 20-09-2010 | Completed | 2010-09-20 | CQPM10001100 | (01) OTD Milestones - Contract Effective Date
task_id | Forecast | STATUS_CODE | Baseline date | TASK_CODE | TASK_NAME | Yesterday
1 | 2020-06-09 | Completed | 2020-06-09 | CS010420 | Stage Gate P7
2 | 2019-06-09 | Completed | 2019-06-07 | CQPM10009390 | (15) OTD Milestones - System Commissioning Complete (Stage 2)
3 | 2019-06-09 | Completed | 2019-06-07 | CQPM10001210 | (16) COTD Milestones - Partial Acceptance Certificate (PAC)
4 | 2019-06-07 | Completed | 2019-06-07 | CQPM10009380 | (14) OTD Milestones - Subsystem Pre-Commissioning Complete
5 | 2019-06-05 | Completed | 2019-06-05 | CQPM10001200 | (13) OTD Milestones - Installation Completed
6 | 2018-01-31 | Completed | 2018-01-31 | CQPM10009370 | (09) OTD Milestones - Detailed Engineering Complete
7 | 2014-09-27 | Completed | 2014-09-26 | CQPM10001150 | (10) OTD Milestones - Manufacture Of All Long Lead Items Complete
8 | 2013-10-28 | Completed | 2013-10-28 | CQPM10001130 | (07) OTD Milestones - Civil Design Issued To Customer
9 | 2012-05-18 | Completed | 2012-05-18 | CQPM10001190 | (12) OTD Milestones - Building Ready For Equipment Installation
10 | 2012-04-05 | Completed | 2012-04-05 | CQPM10009360 | (11) OTD Milestones - FAT of Critical Long Lead Items Complete
11 | 2011-12-23 | Completed | 2011-12-23 | CQPM10009350 | (06) OTD Milestones - Protection & Control System Base Design Complete
12 | 2011-01-10 | Completed | 2011-01-10 | CQPM10001140 | (08) OTD Milestones - Civil Contractor Mobilised On Site
13 | 2011-01-10 | Completed | 2011-01-10 | CQPM70210 | Summary Milestone - Start on site (Stage Gate)
14 | 2010-12-13 | Completed | 2010-12-13 | CQPM10001120 | (04) OTD Milestones - Overall Base Design Completed
15 | 2010-09-24 | Completed | 2010-09-24 | CQPM10001110 | (05) OTD Milestones - P.O for Long Lead-Critical Items Issued
16 | 2010-09-20 | Completed | 2010-09-20 | CQPM10009340 | (03) OTD Milestones - Project Execution Plan (PEP) In Place
17 | 2010-09-20 | Completed | 2010-09-20 | CQPM10009330 | (02) OTD Milestones - Project Management Team Mobilised
18 | 2010-09-20 | Completed | 2010-09-20 | CQPM10001100 | (01) OTD Milestones - Contract Effective Date

## expected visualization
INSTRUCTIONS
With the use of Power BI Desktop create a report with the data available in adjacent worksheets. The report shall present: 1. Slicer to select data date, to see data as per selected snapshot time 2. Slicer to select historical snapshot date, used to populate Historical and Movement column 3. Table with milestone ID, Name, Status, Forecast date, Baseline date, Variance, Historical date, Movement, where Historical date is forecast date from historical snapshot 4. Variance column logic = Baseline - Forecast 5. Movement column logic = Historical - Forecast 6. If there is a new milestone, which doesn't exist in the historical snapshots, Historical and Movement column should be empty 7. For Variance and Movement columns color indicators should be enabled: # if x =>0 Green # if -10<=x<0 Yellow # if x < -10 Red Mock up below. While buidling data model please have in mind scalability (e.g. in future there would be n of snapshots, at the end of every month)

## yesterday snapshot
task_id | Forecast | STATUS_CODE | Baseline date | TASK_CODE | TASK_NAME
1 | 2020-06-09 | Completed | 2020-06-09 | CS010420 | Stage Gate P7
2 | 2019-06-09 | Completed | 2019-06-07 | CQPM10009390 | (15) OTD Milestones - System Commissioning Complete (Stage 2)
3 | 2019-06-09 | Completed | 2019-06-07 | CQPM10001210 | (16) COTD Milestones - Partial Acceptance Certificate (PAC)
4 | 2019-06-07 | Completed | 2019-06-07 | CQPM10009380 | (14) OTD Milestones - Subsystem Pre-Commissioning Complete
5 | 2019-06-05 | Completed | 2019-06-05 | CQPM10001200 | (13) OTD Milestones - Installation Completed
6 | 2018-01-31 | Completed | 2018-01-31 | CQPM10009370 | (09) OTD Milestones - Detailed Engineering Complete
7 | 2014-09-27 | Completed | 2014-09-26 | CQPM10001150 | (10) OTD Milestones - Manufacture Of All Long Lead Items Complete
8 | 2013-10-28 | Completed | 2013-10-28 | CQPM10001130 | (07) OTD Milestones - Civil Design Issued To Customer
9 | 2012-05-18 | Completed | 2012-05-18 | CQPM10001190 | (12) OTD Milestones - Building Ready For Equipment Installation
10 | 2012-04-05 | Completed | 2012-04-05 | CQPM10009360 | (11) OTD Milestones - FAT of Critical Long Lead Items Complete
11 | 2011-12-23 | Completed | 2011-12-23 | CQPM10009350 | (06) OTD Milestones - Protection & Control System Base Design Complete
12 | 2011-01-10 | Completed | 2011-01-10 | CQPM10001140 | (08) OTD Milestones - Civil Contractor Mobilised On Site
13 | 2011-01-10 | Completed | 2011-01-10 | CQPM70210 | Summary Milestone - Start on site (Stage Gate)
14 | 2010-12-13 | Completed | 2010-12-13 | CQPM10001120 | (04) OTD Milestones - Overall Base Design Completed
15 | 2010-09-24 | Completed | 2010-09-24 | CQPM10001110 | (05) OTD Milestones - P.O for Long Lead-Critical Items Issued
16 | 2010-09-20 | Completed | 2010-09-20 | CQPM10009340 | (03) OTD Milestones - Project Execution Plan (PEP) In Place
17 | 2010-09-20 | Completed | 2010-09-20 | CQPM10009330 | (02) OTD Milestones - Project Management Team Mobilised
18 | 2010-09-20 | Completed | 2010-09-20 | CQPM10001100 | (01) OTD Milestones - Contract Effective Date

## end of September snapshot
task_id | Forecast | STATUS_CODE | Baseline date | TASK_CODE | TASK_NAME
1 | 2020-08-09 | Completed | 2020-06-09 | CS010420 | Stage Gate P7
2 | 2019-03-09 | Completed | 2019-06-07 | CQPM10009390 | (15) OTD Milestones - System Commissioning Complete (Stage 2)
4 | 2019-04-07 | Completed | 2019-06-07 | CQPM10009380 | (14) OTD Milestones - Subsystem Pre-Commissioning Complete
5 | 2019-05-05 | Completed | 2019-06-05 | CQPM10001200 | (13) OTD Milestones - Installation Completed
6 | 31/02/2018 | Completed | 2018-01-31 | CQPM10009370 | (09) OTD Milestones - Detailed Engineering Complete
7 | 2014-01-27 | Completed | 2014-09-26 | CQPM10001150 | (10) OTD Milestones - Manufacture Of All Long Lead Items Complete
8 | 2013-11-28 | Completed | 2013-10-28 | CQPM10001130 | (07) OTD Milestones - Civil Design Issued To Customer
9 | 2012-05-18 | Completed | 2012-05-18 | CQPM10001190 | (12) OTD Milestones - Building Ready For Equipment Installation
10 | 2012-04-05 | Completed | 2012-04-05 | CQPM10009360 | (11) OTD Milestones - FAT of Critical Long Lead Items Complete
11 | 2011-12-23 | Completed | 2011-12-23 | CQPM10009350 | (06) OTD Milestones - Protection & Control System Base Design Complete
12 | 2011-01-10 | Completed | 2011-01-10 | CQPM10001140 | (08) OTD Milestones - Civil Contractor Mobilised On Site
13 | 2011-01-10 | Completed | 2011-01-10 | CQPM70210 | Summary Milestone - Start on site (Stage Gate)
14 | 2010-12-13 | Completed | 2010-12-13 | CQPM10001120 | (04) OTD Milestones - Overall Base Design Completed
15 | 2010-09-24 | Completed | 2010-09-24 | CQPM10001110 | (05) OTD Milestones - P.O for Long Lead-Critical Items Issued
16 | 2010-09-20 | Completed | 2010-09-20 | CQPM10009340 | (03) OTD Milestones - Project Execution Plan (PEP) In Place
17 | 2010-09-20 | Completed | 2010-09-20 | CQPM10009330 | (02) OTD Milestones - Project Management Team Mobilised
18 | 2010-09-20 | Completed | 2010-09-20 | CQPM10001100 | (01) OTD Milestones - Contract Effective Date

## end of August snapshot
task_id | Forecast | STATUS_CODE | Baseline date | TASK_CODE | TASK_NAME
1 | 2020-08-09 | Completed | 2020-06-09 | CS010420 | Stage Gate P7
2 | 2019-03-09 | Completed | 2019-06-07 | CQPM10009390 | (15) OTD Milestones - System Commissioning Complete (Stage 2)
4 | 2019-04-07 | Completed | 2019-06-07 | CQPM10009380 | (14) OTD Milestones - Subsystem Pre-Commissioning Complete
5 | 2019-05-05 | Completed | 2019-06-05 | CQPM10001200 | (13) OTD Milestones - Installation Completed
6 | 31/02/2018 | Completed | 2018-01-31 | CQPM10009370 | (09) OTD Milestones - Detailed Engineering Complete
7 | 2014-01-27 | Completed | 2014-09-26 | CQPM10001150 | (10) OTD Milestones - Manufacture Of All Long Lead Items Complete
8 | 2013-11-28 | Completed | 2013-10-28 | CQPM10001130 | (07) OTD Milestones - Civil Design Issued To Customer
9 | 2012-05-18 | Completed | 2012-05-18 | CQPM10001190 | (12) OTD Milestones - Building Ready For Equipment Installation
10 | 2012-04-05 | Completed | 2012-04-05 | CQPM10009360 | (11) OTD Milestones - FAT of Critical Long Lead Items Complete
11 | 2011-12-23 | Completed | 2011-12-23 | CQPM10009350 | (06) OTD Milestones - Protection & Control System Base Design Complete
12 | 2011-01-10 | Completed | 2011-01-10 | CQPM10001140 | (08) OTD Milestones - Civil Contractor Mobilised On Site
13 | 2011-01-10 | Completed | 2011-01-10 | CQPM70210 | Summary Milestone - Start on site (Stage Gate)
14 | 2010-12-15 | Completed | 2010-12-13 | CQPM10001120 | (04) OTD Milestones - Overall Base Design Completed
15 | 2010-09-04 | Completed | 2010-09-24 | CQPM10001110 | (05) OTD Milestones - P.O for Long Lead-Critical Items Issued
16 | 2010-09-10 | Completed | 2010-09-20 | CQPM10009340 | (03) OTD Milestones - Project Execution Plan (PEP) In Place
17 | 2010-06-20 | Completed | 2010-09-20 | CQPM10009330 | (02) OTD Milestones - Project Management Team Mobilised
18 | 2010-05-20 | Completed | 2010-09-20 | CQPM10001100 | (01) OTD Milestones - Contract Effective Date